## (Q2) Mar24
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Project Management | Perform high-level management activities for the project, internally at AEGIS | T1.1 | 2024-03-31 | Marinos Tsantekidis | 2 |  |  | 2024-03-31 | In-progress
Scientific and Innovation Management | Collaborate with technical partners and assess current status of components and envisaged progress. Participate in relevant telcos | T1.3 | 2024-03-31 | Marinos Tsantekidis | 5 | Andreas Alexopoulos, Christos Kargatzis | 6 | 2024-03-31 | In-progress
DMP | Fill in and submit the DMP | T1.4 | 2024-03-22 | Marinos Tsantekidis | 1 |  |  | 2024-03-20 | Completed
Challenges/requirements and scenarios refinements | Aid in the elicitation, analysis and documentation of requirements of the intended stakeholders and the refinement of the scenarios’ definitions, as requested by the task leader. Participate in relevant telcos | T2.1 | 2024-03-31 | Marinos Tsantekidis | 5 |  |  | 2024-03-31 | In-progress
Baseline functional and non-functional requirements | Aid in the SotA update and the analysis of the needs of the various users and intended use of CONSOLE, in order to specify system requirements and functionalities, as requested by the task leader. Participate in relevant telcos | T2.2 | 2024-03-31 | Marinos Tsantekidis | 5 |  |  | 2024-03-31 | In-progress
Platform architecture and functionalities | Task leader. Review challenges, technologies, requirements, and interests analysed in tasks T2.1-T2.3, in order to propose a generic architecture. Host and participate in relevant telcos | T2.4 | 2024-03-31 | Marinos Tsantekidis | 7 |  |  | 2024-03-31 | In-progress
Dissemination and communication activities | Aid in the dissemination and communication activities, as requested by the task leader. Participate in relevant telcos | T5.1 | 2024-03-31 | Marinos Tsantekidis | 1 |  |  | 2024-03-31 | In-progress
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on B2: Costas Kalogiros: Please elaborate on the activity/activities to be performed
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on D2: Costas Kalogiros: Please include the deadline of this activity (i.e., as requested by the assigning person)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## (Q2) Apr24
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Project Management | Perform high-level management activities for the project, internally at AEGIS | T1.1 | 2025-03-31 | Marinos Tsantekidis | 2 |  |  | 2024-04-30 | In-progress
DMP Deliverable | Leading the DMP Deliverable. Create questionnaires, distribute them and start writing the deliverable. | T1.4, T1.5 | 2025-04-30 | Marinos Tsantekidis | 5 | Andreas Alexopoulos, Christos Kargatzis | 6 | 2024-04-30 | In-progress
Challenges/requirements and scenarios refinements | Aid in the elicitation, analysis and documentation of requirements of the intended stakeholders and the refinement of the scenarios’ definitions, as requested by the task leader. Participate in relevant telcos | T2.1 | 2024-04-30 | Marinos Tsantekidis | 4 |  |  | 2024-04-30 | In-progress
Stakeholders questionnaire | Review relevant questionnaire as requested by the task leader | T2.1 | 2024-04-02 | Marinos Tsantekidis | 1 |  |  | 2024-04-01 | Completed
Baseline functional and non-functional requirements | Aid in the SotA update and the analysis of the needs of the various users and intended use of CONSOLE, in order to specify system requirements and functionalities, as requested by the task leader. Provide input to the asset requirements table. Participate in relevant telcos. | T2.2 | 2024-04-30 | Marinos Tsantekidis | 5 | Andreas Alexopoulos | 2 | 2024-04-30 | In-progress
Platform architecture and functionalities | Task leader. Review challenges, technologies, requirements, and interests analysed in tasks T2.1-T2.3, in order to propose a generic architecture. Design detailed architecture. Host and participate in relevant telcos. Present AVT. | T2.4 | 2024-04-30 | Marinos Tsantekidis | 10 | Andreas Alexopoulos, Christos Kargatzis | 6 | 2024-04-30 | In-progress
Dissemination and communication activities | Aid in the dissemination and communication activities, as requested by the task leader. Participate in relevant telcos | T5.1 | 2024-04-30 | Marinos Tsantekidis | 1 |  |  | 2024-04-30 | In-progress
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on B2: Costas Kalogiros: Please elaborate on the activity/activities to be performed
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on D2: Costas Kalogiros: Please include the deadline of this activity (i.e., as requested by the assigning person)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## (Q3) May24
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Project Management | Perform high-level management activities for the project, internally at AEGIS | T1.1 | 2024-05-31 | Marinos Tsantekidis | 2 |  |  | 2024-05-31 | In-progress
Scientific and Innovation Management | Collaborate with technical partners and assess current status of components and envisaged progress. Participate in relevant telcos | T1.3 | 2024-05-31 | Marinos Tsantekidis | 5 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 6 | 2024-05-31 | In-progress
Challenges/requirements and scenarios refinements | Aid in the elicitation, analysis and documentation of requirements of the intended stakeholders and the refinement of the scenarios’ definitions, as requested by the task leader. Participate in relevant telcos | T2.1 | 2024-05-31 | Marinos Tsantekidis | 4 |  |  | 2024-05-31 | In-progress
Baseline functional and non-functional requirements | Aid in the SotA update and the analysis of the needs of the various users and intended use of CONSOLE, in order to specify system requirements and functionalities, as requested by the task leader. Provide input to the asset requirements table. Participate in relevant telcos. | T2.2 | 2024-05-31 | Marinos Tsantekidis | 5 | Andreas Alexopoulos | 2 | 2024-05-31 | In-progress
D2.1 | Provide initial input for SotA update, as requested by the task leader. Participate in relevant telcos. | T2.1/T2.2 | 2024-05-15 | Marinos Tsantekidis | 3 |  |  |  | Completed
Platform architecture and functionalities | Task leader. Review challenges, technologies, requirements, and interests analysed in tasks T2.1-T2.3, in order to propose a generic architecture. Design detailed architecture. Coordinate pilto presentations towards user stories/journeys. Host and participate in relevant telcos. Present AVT. | T2.4 | 2024-05-31 | Marinos Tsantekidis | 10 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 6 | 2024-05-31 | In-progress
D2.2 | Deliverable leader. Create initial ToC for D2.2. | T2.4 | 2024-05-31 | Marinos Tsantekidis | 5 |  |  | 2024-05-31 | In-progress
Dissemination and communication activities | Aid in the dissemination and communication activities, as requested by the task leader. Participate in relevant telcos | T5.1 | 2024-05-31 | Marinos Tsantekidis | 1 |  |  | 2024-05-31 | In-progress
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on B2: Costas Kalogiros: Please elaborate on the activity/activities to be performed
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on D2: Costas Kalogiros: Please include the deadline of this activity (i.e., as requested by the assigning person)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## (Q3) Jun24
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Project Management | Perform high-level management activities for the project, internally at AEGIS | T1.1 | 2024-06-30 | Marinos Tsantekidis | 2 |  |  | 2024-06-30 | In-progress
Scientific and Innovation Management | Coordinate technical activities. Collaborate with technical partners and assess current status of components and envisaged progress. Participate in relevant telcos | T1.3 | 2024-06-30 | Marinos Tsantekidis | 2 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 6 | 2024-06-30 | In-progress
Challenges/requirements and scenarios refinements | Aid in the elicitation, analysis and documentation of requirements of the intended stakeholders and the refinement of the scenarios’ definitions, as requested by the task leader. Participate in relevant telcos | T2.1 | 2024-06-30 | Marinos Tsantekidis | 10 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 30 | 2024-06-30 | In-progress
Stakeholders questionnaire | Review relevant questionnaire as requested by the task leader | T2.1 | 2024-06-02 | Marinos Tsantekidis | 1 |  |  | 2024-06-01 | Completed
Baseline functional and non-functional requirements | Aid in the analysis of the needs of the various users and intended use of CONSOLE, in order to specify system requirements and functionalities, as requested by the task leader. Participate in relevant telcos. | T2.2 | 2024-06-30 | Marinos Tsantekidis | 3 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 10 | 2024-06-30 | In-progress
D2.1 | Refine SotA update, as requested by the task leader. Participate in relevant telcos. | T2.1/T2.2 | 2024-06-15 | Marinos Tsantekidis | 2 |  |  | 2024-06-11 | Completed
Platform architecture and functionalities | Task leader. Review challenges, technologies, requirements, and interests analysed in tasks T2.1-T2.3, in order to propose a generic architecture. Design/update detailed architecture. Host and participate in relevant telcos. | T2.4 | 2024-06-30 | Marinos Tsantekidis | 7 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 20 | 2024-06-30 | In-progress
D2.2 | Deliverable leader. Provide and coordinate collection of input in D2.2. | T2.4 | 2024-06-30 | Marinos Tsantekidis | 20 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 20 | 2024-06-30 | In-progress
Developing the technical components | Aid in the refinement activities for the existing individual components, as well as in common activities to adjust the individual components, as requested by the task leader. Participate in relevant telcos | T3.1 | 2024-06-30 | Marinos Tsantekidis | 2 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 10 | 2024-06-30 | In-progress
CONSOLE platform 1st release | Task leader. Identify architectural requirements for the different real-life scenarios, technical components, and training services. Participate in relevant telcos. | T3.2 | 2024-06-30 | Marinos Tsantekidis | 5 | Andreas Alexopoulos, Christos Kargatzis, Costas Oikonomou | 15 | 2024-06-30 | In-progress
D5.1 | Provide input requested by the task leader | T5.1 | 2024-06-25 | Marinos Tsantekidis | 5 |  |  | 2024-06-25 | Completed
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on B2: Costas Kalogiros: Please elaborate on the activity/activities to be performed
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on D2: Costas Kalogiros: Please include the deadline of this activity (i.e., as requested by the assigning person)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## (Q1) Nov24
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on B2: Costas Kalogiros: Please elaborate on the activity/activities to be performed
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on D2: Costas Kalogiros: Please include the deadline of this activity (i.e., as requested by the assigning person)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## (Q1) Dec24
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on B2: Costas Kalogiros: Please elaborate on the activity/activities to be performed
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on D2: Costas Kalogiros: Please include the deadline of this activity (i.e., as requested by the assigning person)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## (Q1) Jan25
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on B2: Costas Kalogiros: Please elaborate on the activity/activities to be performed
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on D2: Costas Kalogiros: Please include the deadline of this activity (i.e., as requested by the assigning person)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## Feb25
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on B2: Costas Kalogiros: Please elaborate on the activity/activities to be performed
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on D2: Costas Kalogiros: Please include the deadline of this activity (i.e., as requested by the assigning person)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## Mar25
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Project Management | Perform high-level management activities for the project, internally at AEGIS | T1.1 | 2025-03-31 | Nikolaos Gkatzios |  |  |  | 2027-10-31 | In-progress
DMP Deliverable | Leading D1.2 (DMP). Create questionnaires, distribute them and start writing the deliverable. | T1.4, T1.5 | 2025-04-30 | Nikolaos Gkatzios |  | Stavros Tsipras, Georgia Tsipras |  | 2027-10-31 | In-progress
Communication & Dissemination | Task Leaders: Maintain/Update the website, Post on all social media accounts | T2.1 | 2025-03-31 | Nikolaos Gkatzios |  | Jihane Najar |  | 2026-06-30 | In-progress
Deliverable 2.1 | Leading D2.1. Creating a first draft of the deliverable. | T2.1 | 2025-04-30 | Nikolaos Gkatzios |  | Jihane Najar |  | 2025-08-31 | In-progress
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## Apr25
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Project Management | Perform high-level management activities for the project, internally at AEGIS | T1.1 | 2025-03-31 | Nikolaos Gkatzios |  |  |  | 2027-10-31 | In-progress
DMP Deliverable | Leading D1.2 (DMP). Create questionnaires, distribute them and start writing the deliverable. | T1.4, T1.5 | 2025-04-30 | Nikolaos Gkatzios |  | Stavros Tsipras, Georgia Tsipras |  | 2027-10-31 | Completed
Communication & Dissemination | Task Leaders: Maintain/Update the website, Post on all social media accounts | T2.1 | 2025-03-31 | Nikolaos Gkatzios |  | Jihane Najar |  | 2026-06-30 | In-progress
Deliverable 2.1 | Leading D2.1. Creating a first draft of the deliverable. | T2.1 | 2025-04-30 | Nikolaos Gkatzios |  | Jihane Najar |  | 2025-08-31 | Completed
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## May25
Up-to-date information
Activity short name | Detailed description | Related Task (from GA) | Due Date | Project Manager (PM) | PM's planned effort per activity for current month (in hours) | Other contributors (free text) | Rest contributors' planned effort per activity for current month (in hours) | Expected End date | Status
Project Management | Perform high-level management activities for the project, internally at AEGIS | T1.1 | 2025-03-31 | Jihane Najar |  |  |  | 2027-10-31 | In-progress
Technical Requirements | Review and contribute to the Technical Requirements | T3.1 |  | Stella Markopoulou |  | Jihane Najar |  |  | In-progress
Communication & Dissemination | Task Leaders: Maintain/Update the website, Post on all social media accounts | T2.1 | 2025-03-31 | JihaneNajar |  | Jihane Najar |  | 2026-06-30 | In-progress
Communication & Dissemination materials | Creation of the Flyer and the roll-up banner | T2.1 | 2025-05-23 | Jihane Najar |  | George Alymaras |  | 2025-05-15 | Completed
Newsletter #1 | Prepare the first newsletter | T2.1 | 2025-06-15 | Jihane Najar |  | George Alymaras, Alex Katsenos |  | 2025-06-15 | In-progress
Note on A2: Costas Kalogiros: Please provide a succinct name for the activity. New activities should be added on a daily basis (i.e., as soon as a new request emerges or a planned activity should start)
Note on C2: Costas Kalogiros: Please include the most relevant task according to the GA. Note that this task needs to be "active" and AEGIS to be an official contributor (i.e., AEGIS was allocated effort in that task)
Note on F2: Costas Kalogiros: Please include an estimate of the effort required by the PM. Estimates can be revised during activity execution.
Note on G2: Costas Kalogiros: Please include the names of rest contributors, such as the names of supporting PMs, ENGs, legal, Dissemination/Communication/Exploitation etc.
Note on H2: Costas Kalogiros: Please include an estimate of the effort required by the rest contributors. Estimates can be revised during activity execution.
Note on I2: Costas Kalogiros: Please include an estimate of the activity's closure time (i.e., when AEGIS expects that it will be concluded)
Note on J2: Costas Kalogiros: Please choose the most relevant status entry from the list. The status should be revised to be up-to-date

## Table
Name | Status
Admir Jukan | JustAnnounced
Apostolis Zarras | In-progress
Aris Sotiropoulos | Completed
Chronis Ballas | Cancelled
Costas Kalogiros | Paused
Dora Kallipollitou
Ilias Spais
Maria Bouloukaki
Maria Zoidi
Marina Papaefthymiou
Marinos Tsantekidis
Mike Vakallelis
Miltos Kokkonidis
Mohammad Hamad
Nikos Kostalas
Spiros Fotis
Spyros Vantolas
Stathis Dimakos
Stella Markopoulou
Vasilis Tountopoulos