## PartnersInfo
# | Name | Short Name | Country | Type | PIC | PM Rate | Audit cost (if needed) | Reimbursement rate | Target funding | Status | PartA | Role | Comments | Contact
1 | EREVNITIKO PANEPISTIMIAKO INSTITOUTO SYSTIMATON EPIKOINONION KAI YPOLOGISTON (coordinator) | ICCS | EL | Research | 999654356 | 5000 |  | 100% | 500000 | Accepted |  |  |  | tserpes@hua.gr
2 | RESEARCH CENTER ATHENA Industrial System Institute | ISI | EL | Research | 999562788 | 5000 |  | 100% | 450000 | Accepted |  |  |  | Apostolos Fournaris, fournaris @isi.gr Evangelos Haleplidis, haleplidis@isi.gr
3 | UNIVERSITY OF CAGLIARI | UNICA | IT | Research | 999841663 | 5000 |  | 100% | 350000 | Accepted |  |  |  | Battista Biggio battista.biggio@unica.it Maura Pintor maura.pintor@unica.it Giorgio Fumera fumera@unica.it
4 | INSTITUT MINES-TELECOM | IMT | FR | Research | 999849326 | 6500 |  | 100% | 300000 | Accepted |  |  |  | georgios.bouloukakis@telecom-sudparis.eu Houssam Hajj-Hassan, team member, houssam.hajj_hassan@telecom-sudparis.eu
5 | SIEMENS AKTIENGESELLSCHAFT | SIE | DE | Industry | 999987260 | 12180 |  | 100% | 600000 | Accepted |  | Tech provider / Pilot provider |  | Broering, Arne <arne.broering@siemens.com>
6 | AEGIS IT RESEARCH GMBH | AEGIS | DE | SME | 911867804 | 7400 |  | 100% | 450000 | Accepted |  |  |  | hspais@aegisresearch.eu
7 | TELEFONICA | TID | ES | Industry | 917790915 | 7513.6 |  | 100% | 650000 | Accepted |  |  |  | ioannis.arapakis@telefonica.com
8 | UNIVERSITA DI PISA | UNIPI | IT | Research | 999862712 | 4700 |  | 100% | 350000 | Accepted |  |  |  | Davide Bacciu - Università di Pisa <davide.bacciu@unipi.it>
9 | SAP SE | SAP | DE | Industry | 999911212 | 8000 |  | 100% | 500000 | Accepted |  |  |  | francesco.di.cerbo@sap.com, Michele Bezzi (michele.bezzi@sap.com)
10 | SECURITY LABS CONSULTING LIMITED | SLC | IE | SME | 895392645 | 6100 |  | 100% | 300000 | Accepted |  |  |  | spyrospapastergiou@gmail.com, stellioudina@gmail.com
11 | PANASONIC AUTOMOTIVE | PAN | DE | Industry | 985812456 | 12130 |  | 100% | 350000 | Accepted |  | Pilot Provider |  | Petros Kapsalas, petros.kapsalas@eu.panasonic.com
12 | AVISENSE | AVI | EL | SME | 881486337 | 5500 |  | 100% | 400000 | Accepted |  | Pilot Provider |  | Gerasimos Arvanitis, arvanitis@avisense.ai Aris Lalos, lalos@avisense.ai
13 | DIENEKES S.I. SINGLE MEMBER P.C. | DIE | EL | SME | 884438338 | 6500 |  | 100% | 400000 | Accepted |  | Tech Provider |  | sotiris@diienekes.gr
14 | CYBERALYTICS LTD | CBRL | CY | SME | 886488239 | 8500 |  | 100% | 400000 | Accepted |  |  |  | Andreas Miaoudakis a.miaoudakis@cyberalytics.com Tzortzia Koutsouri t.koutsouri¦@cyberalytics.com
15 | SPHYNX TECHNOLOGY SOLUTIONS AG | STS | CH | SME | 881338703 | 17600 |  | 0% | 500000 | Accepted |  | Model driven data analytics services | Data and system security | Michalis Smyrlis smyrlis@sphynx.ch
16
17
18
19
20
21
22
23
|  |  |  | Type of Partner |  |  |  | Accepted | 15
|  |  |  | Research | 5 |  |  | Invited | 0
|  |  |  | Industry | 4 |  |  | Considered | 0
|  |  |  | SME | 6 |  |  | Total | 15
|  |  |  | Total | 15
[8 empty] | Target Funding | 6000000
[8 empty] | Min Funding | 4000000
[8 empty] | Max Funding | 6000000

## Gantt
No | Title | Start M | End M | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 | Project Management | 1 | 36
T1.1 | Project coordination and reporting | 1 | 36
T1.2 | Scientific and technical coordination, and monitoring of project's achievements | 1 | 36
T1.3 | Quality assurance, gender equality assessment and risk management | 1 | 36
T1.4 | Innovation tracking and data management | 1 | 36
T1.5 | Ethical principles and European regulations, fundamental rights, and social sciences | 1 | 36
WP2 | Dissemination, Exploitation, Sustainability | 1 | 36
T2.1 | Outreach planning, Communication and Dissemination | 1 | 36
T2.2 | Standardization activities | 1 | 36
T2.3 | Liaison with other EU-funded projects and initiatives | 1 | 36
T2.4 | Exploitation activities and long-term sustainability | 8 | 36
T2.5 | End user internal organization training activities | 12 | 36
WP3 | Specification/ Requirements and CoEvolution Architecture | 1 | 12
T3.1 | State-of-the-Art, Threat model and Technical Specifications | 1 | 12
T3.2 | Use-Case specifications and Requirements | 1 | 12
T3.3 | CoEvolution Reference Architecture | 1 | 12
T3.4 | Data requirements and Collection | 1 | 12
WP4 | AI model STR Αssessment., Εnhancement and Context Awareness technology enablers | 8 | 33
T4.1 | Adversarial Attack Security Testing/Assessment techniques | 8 | 33
T4.2 | Design and Training Phase Defences Technologies | 8 | 33
T4.3 | Deployment Phase Defenses Technologies | 8 | 33
T4.4 | AI Model Context-Awareness Enablers for Security, Robustness and Performance | 8 | 33
T4.5 | Continuous Post-Deployment Defense through Incremental training technologies | 8 | 33
WP5 | CoEvolution AI model lifecycle STR Security Assurance and Monitoring | 8 | 33
T5.1 | STR AI Model Bills-of-Material Definition, Design and Management | 8 | 33
T5.2 | Security Runtime Monitoring | 8 | 33
T5.3 | Risk Assessement Analysis and Security Assessment Engines | 8 | 33
T5.4 | Continuous Security Assurance and Trusted AIMBOM Generation Mechanism | 8 | 33
T5.5 | Evolutionary strategies for context-awareness adaptation | 8 | 33
WP6 | Integration, evaluation and project outcomes | 6 | 36
T6.1 | CoEvolution hub Integration and Implementation | 19 | 33
T6.2 | Simulation for evaluation and dataset creation | 6 | 24
T6.3 | Pilot Deployment, Testing and Demonstration | 24 | 34
T6.4 | Validation, Evaluation and project outcomes | 30 | 36
Mil: MVP

## Contributions
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
No | Title | Start M | End M | Lead | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
WP1 | Project Management | 1 | 36 | 1 | 1: WPL | Legend
T1.1 | Project coordination and reporting | 1 | 36 | 1 | [15 empty] | WPL | WP Leader | bar: 1
T1.2 | Scientific and technical coordination, and monitoring of project's achievements | 1 | 36 | 1 | [15 empty] | TL | Task Leader | bar: 2
T1.3 | Quality assurance, gender equality assessment and risk management | 1 | 36 | 1 | [15 empty] | C | Task Contributor | bar: 1
T1.4 | Innovation tracking and data management | 1 | 36 | 1 | bar: 6
T1.5 | Ethical principles and European regulations, fundamental rights, and social sciences | 1 | 36 | 1 | bar: 6
WP2 | Dissemination, Exploitation, Sustainability | 1 | 36 | 1 | 14: WPL
T2.1 | Outreach planning, Communication and Dissemination | 1 | 36 | 1 | bar: 6
T2.2 | Standardization activities | 1 | 36 | 1 | bar: 14
T2.3 | Liaison with other EU-funded projects and initiatives | 1 | 36 | 1 | bar: 2
T2.4 | Exploitation activities and long-term sustainability | 8 | 36 | 1 | bar: 11
T2.5 | End user internal organization training activities | 12 | 36 | 1 | bar: 5
WP3 | Specification/ Requirements and CoEvolution Architecture | 1 | 12 | 1 | 7: WPL
T3.1 | State-of-the-Art, Threat model and Technical Specifications | 1 | 12 | 1 | bar: 9
T3.2 | Use-Case specifications and Requirements | 1 | 12 | 1 | bar: 11
T3.3 | CoEvolution Reference Architecture | 1 | 12 | 1 | bar: 2
T3.4 | Data requirements and Collection | 1 | 12 | 1 | bar: 13
WP4 | AI model STR Αssessment., Εnhancement and Context Awareness technology enablers | 8 | 33 | 1 | 7: WPL
T4.1 | Adversarial Attack Security Testing/Assessment techniques | 8 | 33 | 1 | bar: 12
T4.2 | Design and Training Phase Defences Technologies | 8 | 33 | 1 | bar: 3
T4.3 | Deployment Phase Defenses Technologies | 8 | 33 | 1 | bar: 7
T4.4 | AI Model Context-Awareness Enablers for Security, Robustness and Performance | 8 | 33 | 1 | bar: 7
T4.5 | Continuous Post-Deployment Defense through Incremental training technologies | 8 | 33 | 1 | bar: 8
WP5 | CoEvolution AI model lifecycle STR Security Assurance and Monitoring | 8 | 33 | 1 | 13: WPL
T5.1 | STR AI Model Bills-of-Material Definition, Design and Management | 8 | 33 | 1 | bar: 2
T5.2 | Security Runtime Monitoring | 8 | 33 | 1 | bar: 6
T5.3 | Risk Assessement Analysis and Security Assessment Engines | 8 | 33 | 1 | bar: 10
T5.4 | Continuous Security Assurance and Trusted AIMBOM Generation Mechanism | 8 | 33 | 1 | bar: 14
T5.5 | Evolutionary strategies for context-awareness adaptation | 8 | 33 | 1 | bar: 7
WP6 | Integration, evaluation and project outcomes | 6 | 36 | 1 | 12: WPL
T6.1 | CoEvolution hub Integration and Implementation | 19 | 33 | 1 | bar: 6
T6.2 | Simulation for evaluation and dataset creation | 6 | 24 | 1 | bar: 12
T6.3 | Pilot Deployment, Testing and Demonstration | 24 | 34 | 1 | bar: 5
T6.4 | Validation, Evaluation and project outcomes | 30 | 36 | 1 | bar: 10
|  |  |  | WPL | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
|  |  |  | TL | 2 | 4 | 1 | 0 | 2 | 5 | 3 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 0
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## WP1 (hidden)
Number of tasks | Work Package Number | #VALUE! | [7 empty] | Lead beneficiary |  |  |  | #VALUE!
| Work Package Title | #VALUE!
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR!
| Start month | #VALUE! 1 ICCS: #VALUE!; #VALUE! 8 UNIPI: End month; #VALUE! 15 STS: #VALUE!
-1 | Objectives
Description of Work
1 | Delete this task
2 | Delete this task
3 | Delete this task
4 | Delete this task
5 | Delete this task
6 | Delete this task
7 | Delete this task
8 | Delete this task
9 | Delete this task
10 | Delete this task
Deliverables

## WP2 (hidden)
Number of tasks | Work Package Number | #VALUE! | [7 empty] | Lead beneficiary |  |  |  | #VALUE!
| Work Package Title | #VALUE!
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR!
| Start month | #VALUE! 1 ICCS: #VALUE!; #VALUE! 8 UNIPI: End month; #VALUE! 15 STS: #VALUE!
-1 | Objectives
Description of Work
1 | Delete this task
2 | Delete this task
3 | Delete this task
4 | Delete this task
5 | Delete this task
6 | Delete this task
7 | Delete this task
8 | Delete this task
9 | Delete this task
10 | Delete this task
Deliverables

## WP3 (hidden)
Number of tasks | Work Package Number | #VALUE! | [7 empty] | Lead beneficiary |  |  |  | #VALUE!
| Work Package Title | #VALUE!
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR!
| Start month | #VALUE! 1 ICCS: #VALUE!; #VALUE! 8 UNIPI: End month; #VALUE! 15 STS: #VALUE!
-1 | Objectives
Description of Work
1 | Delete this task
2 | Delete this task
3 | Delete this task
4 | Delete this task
5 | Delete this task
6 | Delete this task
7 | Delete this task
8 | Delete this task
9 | Delete this task
10 | Delete this task
Deliverables

## WP4 (hidden)
Number of tasks | Work Package Number | #VALUE! | [7 empty] | Lead beneficiary |  |  |  | #VALUE!
| Work Package Title | #VALUE!
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR!
| Start month | #VALUE! 1 ICCS: #VALUE!; #VALUE! 8 UNIPI: End month; #VALUE! 15 STS: #VALUE!
-1 | Objectives
Description of Work
1 | Delete this task
2 | Delete this task
3 | Delete this task
4 | Delete this task
5 | Delete this task
6 | Delete this task
7 | Delete this task
8 | Delete this task
9 | Delete this task
10 | Delete this task
Deliverables

## WP5 (hidden)
Number of tasks | Work Package Number | #VALUE! | [7 empty] | Lead beneficiary |  |  |  | #VALUE!
| Work Package Title | #VALUE!
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR!
| Start month | #VALUE! 1 ICCS: #VALUE!; #VALUE! 8 UNIPI: End month; #VALUE! 15 STS: #VALUE!
-1 | Objectives
Description of Work
1 | Delete this task
2 | Delete this task
3 | Delete this task
4 | Delete this task
5 | Delete this task
6 | Delete this task
7 | Delete this task
8 | Delete this task
9 | Delete this task
10 | Delete this task
Deliverables

## WP6 (hidden)
Number of tasks | Work Package Number | #VALUE! | [7 empty] | Lead beneficiary |  |  |  | #VALUE!
| Work Package Title | #VALUE!
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR!
| Start month | #VALUE! 1 ICCS: #VALUE!; #VALUE! 8 UNIPI: End month; #VALUE! 15 STS: #VALUE!
-1 | Objectives
Description of Work
1 | Delete this task
2 | Delete this task
3 | Delete this task
4 | Delete this task
5 | Delete this task
6 | Delete this task
7 | Delete this task
8 | Delete this task
9 | Delete this task
10 | Delete this task
Deliverables

## WP7 (hidden)
Number of tasks | Work Package Number | #VALUE! | [7 empty] | Lead beneficiary |  |  |  | #VALUE!
| Work Package Title | #VALUE!
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR!
| Start month | #VALUE! 1 ICCS: #VALUE!; #VALUE! 8 UNIPI: End month; #VALUE! 15 STS: #VALUE!
-1 | Objectives
Description of Work
1 | Delete this task
2 | Delete this task
3 | Delete this task
4 | Delete this task
5 | Delete this task
6 | Delete this task
7 | Delete this task
8 | Delete this task
9 | Delete this task
10 | Delete this task
Deliverables

## WP8 (hidden)
Number of tasks | Work Package Number | #VALUE! | [7 empty] | Lead beneficiary |  |  |  | #VALUE!
| Work Package Title | #VALUE!
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR!
| Start month | #VALUE! 1 ICCS: #VALUE!; #VALUE! 8 UNIPI: End month; #VALUE! 15 STS: #VALUE!
-1 | Objectives
Description of Work
1 | Delete this task
2 | Delete this task
3 | Delete this task
4 | Delete this task
5 | Delete this task
6 | Delete this task
7 | Delete this task
8 | Delete this task
9 | Delete this task
10 | Delete this task
Deliverables

## WPs
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | Show C | 0.0
No | Title | Start M | End M | Leader Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS | Total /Task |  |  | Task Data
WP1 | Project Management | 1 | 36 | ICCS | 1 ICCS: WPL |  | 48 | WP1
T1.1 | Project coordination and reporting | 1 | 36 | ICCS | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 29 | 6.997% | WP1 | Task 1.1: Project coordination and reporting; (Leader: ICCS; Participants: All; M01-M36)
T1.2 | Scientific and technical coordination, and monitoring of project's achievements | 1 | 36 | ISI | 2 ISI: 6 | 6 |  | WP1 | Task 1.2: Scientific and technical coordination, and monitoring of project's achievements; (Leader: ISI; Participants: ISI; M01-M36)
T1.3 | Quality assurance, gender equality assessment and risk management | 1 | 36 | ICCS | 1 ICCS: 4; 7 TID: 1 | 5 |  | WP1 | Task 1.3: Quality assurance, gender equality assessment and risk management; (Leader: ICCS; Participants: ICCS, TID; M01-M36)
T1.4 | Innovation tracking and data management | 1 | 36 | AEGIS | 6 AEGIS: 3 | 3 |  | WP1 | Task 1.4: Innovation tracking and data management; (Leader: AEGIS; Participants: AEGIS; M01-M36)
T1.5 | Ethical principles and European regulations, fundamental rights, and social sciences | 1 | 36 | AEGIS | 2 ISI: 1; 6 AEGIS: 3; 7 TID: 1 | 5 |  | WP1 | Task 1.5: Ethical principles and European regulations, fundamental rights, and social sciences; (Leader: AEGIS; Participants: ISI, AEGIS, TID; M01-M36)
WP2 | Dissemination, Exploitation, Sustainability | 1 | 36 | CBRL | 14 CBRL: WPL |  | 90 | WP2
T2.1 | Outreach planning, Communication and Dissemination | 1 | 36 | AEGIS | 2 | 2 | 2 | 2 | 2 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 36 | 13.12% | WP2 | Task 2.1: Outreach planning, Communication and Dissemination; (Leader: AEGIS; Participants: All; M01-M36)
T2.2 | Standardization activities | 1 | 36 | CBRL | 2 ISI: 1; 5 SIE: 2; 7 TID: 1; 9 SAP: 1; 11 PAN: 2; 14 CBRL: 6; 15 STS: 2 | 15 |  | WP2 | Task 2.2: Standardization activities; (Leader: CBRL; Participants: ISI, SIE, TID, SAP, PAN, CBRL; M01-M36)
T2.3 | Liaison with other EU-funded projects and initiatives | 1 | 36 | ISI | 2 ISI: 4; 4 IMT: 2; 13 DIE: 2; 14 CBRL: 2; 15 STS: 2 | 12 |  | WP2 | Task 2.3: Liaison with other EU-funded projects and initiatives ; (Leader: ISI; Participants: ISI, IMT, DIE, CBRL; M01-M36)
T2.4 | Exploitation activities and long-term sustainability | 8 | 36 | PAN |  |  |  |  | 2 |  | 2 |  | 3 | 2 | 4 | 2 | 2 | 2 | 2 | 21 |  | WP2 | Task 2.4: Exploitation activities and long-term sustainability; (Leader: PAN; Participants: SIE, TID, SAP, SLC, PAN, AVI, DIE, CBRL; M08-M36)
T2.5 | End user internal organization training activities | 12 | 36 | SIE | 5 SIE: 3; 9 SAP: 1; 11 PAN: 2 | 6 |  | WP2
WP3 | Specification/ Requirements and CoEvolution Architecture | 1 | 12 | ISI | 2 ISI: WPL |  | 63 | WP3
T3.1 | State-of-the-Art, Threat model and Technical Specifications | 1 | 12 | SAP |  | 2 | 2 | 1 |  | 1 | 2 | 1 | 4 | 1 |  |  | 1 | 1 |  | 16 | 9.184% | WP3 | Task 3.1: State-of-the-Art, Threat model and Technical Specifications; (Leader: SAP; Participants: ISI, UNICA, IMT, AEGIS, TID, UNIPI, SAP, SLC, DIE, CBRL; M01-M12)
T3.2 | Use-Case specifications and Requirements | 1 | 12 | PAN |  |  |  |  | 3 | 1 |  |  | 1 | 1 | 4 | 3 | 1 | 1 | 2 | 17 |  | WP3 | Task 3.2: Use-Case specifications and Requirements; (Leader: PAN; Participants: SIE, AEGIS, SAP, SLC, PAN, AVI, DIE, CBRL; M01-M12)
T3.3 | CoEvolution Reference Architecture | 1 | 12 | ISI | 1 ICCS: 2; 2 ISI: 6; 3 UNICA: 2; 4 IMT: 2; 6 AEGIS: 2; 8 UNIPI: 2; 9 SAP: 2; 14 CBRL: 2 | 20 |  | WP3 | Task 3.3: CoEvolution Reference Architecture; (Leader: ISI; Participants: ICCS, ISI, UNICA, IMT, AEGIS, UNIPI, SAP, CBRL; M01-M12)
T3.4 | Data requirements and Collection | 1 | 12 | DIE | 2 ISI: 2; 6 AEGIS: 2; 10 SLC: 2; 13 DIE: 4 | 10 |  | WP3 | Task 3.4: Data requirements and Collection; (Leader: DIE; Participants: ISI, AEGIS, SLC, DIE; M01-M12)
WP4 | AI model STR Αssessment., Εnhancement and Context Awareness technology enablers | 8 | 33 | TID | 7 TID: WPL |  | 210 | WP4
T4.1 | Adversarial Attack Security Testing/Assessment techniques | 8 | 33 | AVI | 2 ISI: 6; 4 IMT: 8; 5 SIE: 3; 9 SAP: 6; 11 PAN: 2; 12 AVI: 18 | 43 | 30.61% | WP4 | Task 4.1: Adversarial Attack Security Testing/Assessment techniques; (Leader: AVI; Participants: ISI, IMT, SIE, SAP, PAN, AVI; M08-M33)
T4.2 | Design and Training Phase Defences Technologies | 8 | 33 | UNICA | 1 ICCS: 9; 2 ISI: 4; 3 UNICA: 18; 8 UNIPI: 10; 9 SAP: 12; 11 PAN: 2 | 55 |  | WP4 | Task 4.2: Design and Training Phase Defences Technologies; (Leader: UNICA; Participants: ICCS, ISI, UNICA, UNIPI, SAP, PAN; M08-M33)
T4.3 | Deployment Phase Defenses Technologies | 8 | 33 | TID | 1 ICCS: 9; 2 ISI: 4; 3 UNICA: 6; 5 SIE: 3; 7 TID: 12; 11 PAN: 2 | 36 |  | WP4 | Task 4.3: Deployment Phase Defenses Technologies; (Leader: TID; Participants: ICCS, ISI, UNICA, SIE, TID, PAN; M08-M33)
T4.4 | AI Model Context-Awareness Enablers for Security, Robustness and Performance | 8 | 33 | TID | 4 IMT: 8; 7 TID: 21 | 29 |  | WP4 | Task 4.4: AI Model Context-Awareness Enablers for Security, Robustness and Performance; (Leader: TID; Participants: IMT, TID; M08-M33)
T4.5 | Continuous Post-Deployment Defense through Incremental training technologies | 8 | 33 | UNIPI | 3 UNICA: 9; 5 SIE: 4; 8 UNIPI: 18; 9 SAP: 6; 12 AVI: 6; 13 DIE: 4 | 47 |  | WP4 | Task 4.5: Continuous Post-Deployment Defense through Incremental training technologies; (Leader: UNIPI; Participants: UNICA, SIE, UNIPI, SAP, AVI, DIE; M08-M33)
WP5 | CoEvolution AI model lifecycle STR Security Assurance and Monitoring | 8 | 33 | DIE | 13 DIE: WPL |  | 131 | WP5
T5.1 | STR AI Model Bills-of-Material Definition, Design and Management | 8 | 33 | ISI | 2 ISI: 12; 6 AEGIS: 2; 8 UNIPI: 9; 15 STS: 5 | 28 | 19.1% | WP5 | Task 5.1: STR AI Model Bills-of-Material Definition, Design and Management; (Leader: ISI; Participants: ISI, AEGIS, UNIPI; M08-M33)
T5.2 | Security Runtime Monitoring | 8 | 33 | DIE | 1 ICCS: 8; 2 ISI: 2; 6 AEGIS: 8; 12 AVI: 6; 13 DIE: 12 | 36 |  | WP5 | Task 5.2: Security Runtime Monitoring; (Leader: DIE; Participants: ICCS, ISI, AEGIS, AVI, DIE; M08-M33)
T5.3 | Risk Assessement Analysis and Security Assessment Engines | 8 | 33 | SLC | 1 ICCS: 8; 2 ISI: 2; 10 SLC: 16; 13 DIE: 4 | 30 |  | WP5 | Task 5.3: Risk Assessement Analysis and Security Assessment Engines; (Leader: SLC; Participants: ICCS, ISI, SLC, DIE; M08-M33)
T5.4 | Continuous Security Assurance and Trusted AIMBOM Generation Mechanism | 8 | 33 | CBRL | 2 ISI: 5; 8 UNIPI: 9; 13 DIE: 4; 14 CBRL: 14; 15 STS: 5 | 37 |  | WP5 | Task 5.4: Continuous Security Assurance and Trusted AIMBOM Generation Mechanism; (Leader: CBRL; Participants: ISI, UNIPI, DIE, CBRL; M08-M33)
T5.5 | Evolutionary strategies for context-awareness adaptation | 8 | 33 | TID | 3 UNICA: 8; 6 AEGIS: 2; 7 TID: 20 | 30 |  | WP5 | Task 5.5: Evolutionary strategies for context-awareness adaptation; (Leader: TID; Participants: UNICA, AEGIS, TID; M08-M33)
WP6 | Integration, evaluation and project outcomes | 6 | 36 | AVI | 12 AVI: WPL |  | 114 | WP6
T6.1 | CoEvolution hub Integration and Implementation | 19 | 33 | AEGIS | 2 | 3 | 2 | 2 | 5 | 8 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 39 | 16.62% | WP6 | Task 6.1: CoEvolution hub Integration and Implementation; (Leader: AEGIS; Participants: All; M19-M33)
T6.2 | Simulation for evaluation and dataset creation | 6 | 24 | AVI | 1 ICCS: 8; 4 IMT: 6; 5 SIE: 5; 12 AVI: 9 | 28 |  | WP6 | Task 6.2: Simulation for evaluation and dataset creation; (Leader: AVI; Participants: ICCS, IMT, SIE, AVI; M06-M24)
T6.3 | Pilot Deployment, Testing and Demonstration | 24 | 34 | SIE | 2 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 33 |  | WP6 | Task 6.3: Pilot Deployment, Testing and Demonstration; (Leader: SIE; Participants: All; M24-M34)
T6.4 | Validation, Evaluation and project outcomes | 30 | 36 | SLC | 10 SLC: 5; 11 PAN: 1; 12 AVI: 4; 13 DIE: 3; 15 STS: 1 | 14 |  | WP6 | Task 6.4: Validation, Evaluation and project outcomes; (Leader: SLC; Participants: SLC, PAN, AVI, DIE; M30-M36)
| PersonMonths / Partner |  |  |  | 69 | 65 | 52 | 34 | 38 | 43 | 67 | 56 | 43 | 34 | 25 | 55 | 44 | 35 | 26 | 686
|  |  |  | Target PMS | 75 | 67 | 52 | 34 | 36 | 45 | 66 | 56 | 47 | 36 | 21 | 55 | 46 | 35 | 21
|  |  |  | Target Funds | 500 | 450 | 350 | 300 | 600 | 450 | 650 | 350 | 500 | 300 | 404.063 | 400 | 400 | 400 | 500
|  |  |  | Actual Funds | 467.5 | 443.75 | 350 | 301.25 | 634.8 | 429 | 660.514 | 354 | 478.25 | 284.25 | 404.063 | 403.125 | 382.5 | 396.875 | 0
[5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
[5 empty] | 6 | 2 | 0 | 0 | -2 | 2 | -1 | 0 | 4 | 2 | -4 | 0 | 2 | 0 | -5
WP/Task
|  | 1 | ICCS | 3
|  | 2 | ISI | 5
|  | 3 | UNICA | 1 | 1 ICCS: Travel Analysis
|  | 4 | IMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Estimated travel costs
|  | 5 | SIE | 2 | [18 empty] | Plenary and review travels for project duration
|  | 6 | AEGIS | 4 | [18 empty] | Persons per Consortium travel
|  | 7 | TID | 4 | [18 empty] | Project technical / user meetings (WP travels) - one person travelling
|  | 8 | UNIPI | 1 | [18 empty] | Additional travels for project duration (dissemination advisory board etc.) - one person travelling
|  | 9 | SAP | 1 | [18 empty] | Average cost (in €) per travel per person
|  | 10 | SLC | 2 | [18 empty] | Claimed travel costs
|  | 11 | PAN | 2
|  | 12 | AVI | 3
|  | 13 | DIE | 3
|  | 14 | CBRL | 3
|  | 15 | STS | 0
|  | 16 |  | 0
|  | 17 |  | 0
|  | 18 |  | 0

## Financial
# | Abrev. | Type | Need Audit? | Rate | Total PMs | A. Personnel costs/€ (a1) | B. Sub- contracting costs/€ (b) | C.1 Travel and Subsistence/€ (c1) | C.2 Equipment/€ (c2) | C.3 Other goods, works and services TOTAL/€ |  |  | (C) Purchase costs | D. Other cost categories | [7 empty] | D. Other cost categories | (E) Indirect Costs (e)=25%*[(a1)+(c1)+(c2)+(c3)+(d7)] | (H) Total eligible costs/€ (h)=(a1)+(b)+(c1)+(c2)+(c3)+(d)+(e) | (U) Funding rate | (J) Max. grant / € (=H*I) | 15% Criterion | Target
[10 empty] | Audit/€ | Other goods, works and services/€ | (c3) TOTAL |  | D.1 Financial support to third parties (Actual costs) (d1) | D.2 Internally invoiced goods and services (Unit costs - usual accounting practices) (d2) | D.3 Transnation al access to research infrastructure s (Unit costs) (d3) | D.4 Virtual access to research infrastructure s (Unit costs) (d4) | [D.5 PCP/PPI procurement costs (Actual costs) (d5) ] | [D.6 Euratom Cofund staff mobility costs (Unit costs) (d6) ] | [D.7 ERC additional funding (Actual costs) (d7) ] (the only one participating to Indirect costs) | [D.8 ERC additional funding (subcontracti ng, FSTP and internally invoiced goods and services) (Actual costs) (d8) ] | [6 empty] | Total | Personnel | PMS
1 | ICCS | Research | Yes | 5000 | 69 | 345000 |  | 20000 | 5000 | 4000 |  | 4000 | 29000 | [8 empty] | 0 | 93500 | 467500 | 100% | 467500 | 8.406% | 500000 | 376800 | 75
2 | ISI | Research | Yes | 5000 | 65 | 325000 |  | 20000 | 5000 | 5000 |  | 5000 | 30000 | [8 empty] | 0 | 88750 | 443750 | 100% | 443750 | 9.231% | 450000 | 336000 | 67
3 | UNICA | Research | No | 5000 | 52 | 260000 |  | 20000 | 0 | 0 |  | 0 | 20000 | [8 empty] | 0 | 70000 | 350000 | 100% | 350000 | 7.692% | 350000 | 264000 | 52
4 | IMT | Research | No | 6500 | 34 | 221000 |  | 20000 | 0 | 0 |  | 0 | 20000 | [8 empty] | 0 | 60250 | 301250 | 100% | 301250 | 9.05% | 300000 | 224000 | 34
5 | SIE | Industry | Yes | 12180 | 38 | 462840 |  | 20000 | 20000 | 5000 |  | 5000 | 45000 | [8 empty] | 0 | 126960 | 634800 | 100% | 634800 | 9.723% | 600000 | 444000 | 36
6 | AEGIS | SME | No | 7400 | 43 | 318200 |  | 20000 | 0 | 5000 |  | 5000 | 25000 | [8 empty] | 0 | 85800 | 429000 | 100% | 429000 | 7.857% | 450000 | 340000 | 45
7 | TID | Industry | Yes | 7513.6 | 67 | 503411.2 |  | 20000 | 0 | 5000 |  | 5000 | 25000 | [8 empty] | 0 | 132102.8 | 660514 | 100% | 660514 | 4.966% | 650000 | 500000 | 66
8 | UNIPI | Research | No | 4700 | 56 | 263200 |  | 20000 | 0 | 0 |  | 0 | 20000 | [8 empty] | 0 | 70800 | 354000 | 100% | 354000 | 7.599% | 350000 | 264000 | 56
9 | SAP | Industry | Yes | 8000 | 43 | 344000 |  | 21600 | 0 | 0 | 17000 | 17000 | 38600 | [8 empty] | 0 | 95650 | 478250 | 100% | 478250 | 11.22% | 500000 | 382720 | 47
10 | SLC | SME | No | 6100 | 34 | 207400 |  | 20000 | 0 | 0 |  | 0 | 20000 | [8 empty] | 0 | 56850 | 284250 | 100% | 284250 | 9.643% | 300000 | 224000 | 36
11 | PAN | Industry | No | 12130 | 25 | 303250 |  | 20000 | 0 | 0 |  | 0 | 20000 | [8 empty] | 0 | 80812.5 | 404062.5 | 100% | 404063 | 6.595% | 350000 | 264000 | 21
12 | AVI | SME | No | 5500 | 55 | 302500 |  | 20000 | 0 | 0 |  | 0 | 20000 | [8 empty] | 0 | 80625 | 403125 | 100% | 403125 | 6.612% | 400000 | 304000 | 55
13 | DIE | SME | No | 6500 | 44 | 286000 |  | 20000 | 0 | 0 |  | 0 | 20000 | [8 empty] | 0 | 76500 | 382500 | 100% | 382500 | 6.993% | 400000 | 304000 | 46
14 | CBRL | SME | No | 8500 | 35 | 297500 |  | 20000 | 0 | 0 |  | 0 | 20000 | [8 empty] | 0 | 79375 | 396875 | 100% | 396875 | 6.723% | 400000 | 304000 | 35
15 | STS | SME | No | 17600 | 26 | 457600 |  | 20000 | 3000 | 10000 |  | 10000 | 33000 | [8 empty] | 0 | 122650 | 613250 | 0% | 0 | 7.212% | 500000 | 373600 | 21
Total |  |  |  |  | 686 | 4896901.2 | 0 | 301600 | 33000 | 34000 | 17000 | 51000 | 385600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320625.3 | 6603126.5 |  | 5989877 | 7.874% | 6000000 | 4531520 | 671

## Totals
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Total /Task
| ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | Total |  | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL
WP1 | 19 | 8 | 1 | 1 | 1 | 7 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 47 | WP1 | 95000 | 40000 | 5000 | 6500 | 12180 | 51800 | 22540.8 | 4700 | 8000 | 6100 | 12130 | 5500 | 6500 | 8500 | 284450.8
WP2 | 2 | 7 | 2 | 4 | 9 | 8 | 5 | 2 | 7 | 4 | 10 | 4 | 6 | 12 | 82 | WP2 | 10000 | 35000 | 10000 | 26000 | 109620 | 59200 | 37568 | 9400 | 56000 | 24400 | 121300 | 22000 | 39000 | 102000 | 661488
WP3 | 2 | 10 | 4 | 3 | 3 | 6 | 2 | 3 | 7 | 4 | 4 | 3 | 6 | 4 | 61 | WP3 | 10000 | 50000 | 20000 | 19500 | 36540 | 44400 | 15027.2 | 14100 | 56000 | 24400 | 48520 | 16500 | 39000 | 34000 | 427987.2
WP4 | 18 | 14 | 33 | 16 | 10 | 0 | 33 | 28 | 24 | 0 | 6 | 24 | 4 | 0 | 210 | WP4 | 90000 | 70000 | 165000 | 104000 | 121800 | 0 | 247948.8 | 131600 | 192000 | 0 | 72780 | 132000 | 26000 | 0 | 1353128.8
WP5 | 16 | 21 | 8 | 0 | 0 | 12 | 20 | 18 | 0 | 16 | 0 | 6 | 20 | 14 | 151 | WP5 | 80000 | 105000 | 40000 | 0 | 0 | 88800 | 150272 | 84600 | 0 | 97600 | 0 | 33000 | 130000 | 119000 | 928272
WP6 | 12 | 5 | 4 | 10 | 15 | 10 | 4 | 4 | 4 | 9 | 4 | 17 | 7 | 4 | 109 | WP6 | 60000 | 25000 | 20000 | 65000 | 182700 | 74000 | 30054.4 | 18800 | 32000 | 54900 | 48520 | 93500 | 45500 | 34000 | 783974.4
| 69 | 65 | 52 | 34 | 38 | 43 | 67 | 56 | 43 | 34 | 25 | 55 | 44 | 35 | 660 |  | 345000 | 325000 | 260000 | 221000 | 462840 | 318200 | 503411.2 | 263200 | 344000 | 207400 | 303250 | 302500 | 286000 | 297500 | 4439301.2
660

## Table3.1a
WP# | WP Title | Lead # | Lead Name | PMs | Start | End | TotalIndex
WP1 | Project Management | 1 | ICCS | 48 | 1 | 36 | 17
WP2 | Dissemination, Exploitation, Sustainability | 14 | CBRL | 90 | 1 | 36
WP3 | Specification/ Requirements and CoEvolution Architecture | 2 | ISI | 63 | 1 | 12
WP4 | AI model STR Αssessment., Εnhancement and Context Awareness technology enablers | 7 | TID | 210 | 8 | 33
WP5 | CoEvolution AI model lifecycle STR Security Assurance and Monitoring | 13 | DIE | 161 | 8 | 33
WP6 | Integration, evaluation and project outcomes | 12 | AVI | 114 | 6 | 36
Total |  |  |  | 686

## Table3.1b_WP Headers (hidden)
Headers | Work Package Number | WP1 | [7 empty] | Lead beneficiary | [5 empty] | ICCS
| Work Package Title | Project Management
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 19 | 8 | 1 | 1 | 1 | 7 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | #ERROR! | #ERROR!
| Start month | Project Management 1 ICCS: 1; Project Management 8 UNIPI: End month; Project Management 15 STS: 36
| Work Package Number | Project Management 1 ICCS: WP2; Project Management 9 SAP: Lead beneficiary; Project Management 15 STS: CBRL
| Work Package Title | Project Management 1 ICCS: Dissemination, Exploitation, Sustainability
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 2 | 7 | 2 | 4 | 9 | 8 | 5 | 2 | 7 | 4 | 10 | 4 | 6 | 12 | #ERROR! | #ERROR!
| Start month | Dissemination, Exploitation, Sustainability 1 ICCS: 1; Dissemination, Exploitation, Sustainability 8 UNIPI: End month; Dissemination, Exploitation, Sustainability 15 STS: 36
| Work Package Number | Dissemination, Exploitation, Sustainability 1 ICCS: WP3; Dissemination, Exploitation, Sustainability 9 SAP: Lead beneficiary; Dissemination, Exploitation, Sustainability 15 STS: ISI
| Work Package Title | Dissemination, Exploitation, Sustainability 1 ICCS: Specification/ Requirements and CoEvolution Architecture
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 2 | 10 | 4 | 3 | 3 | 6 | 2 | 3 | 7 | 4 | 4 | 3 | 6 | 4 | #ERROR! | #ERROR!
| Start month | Specification/ Requirements and CoEvolution Architecture 1 ICCS: 1; Specification/ Requirements and CoEvolution Architecture 8 UNIPI: End month; Specification/ Requirements and CoEvolution Architecture 15 STS: 12
| Work Package Number | Specification/ Requirements and CoEvolution Architecture 1 ICCS: WP4; Specification/ Requirements and CoEvolution Architecture 9 SAP: Lead beneficiary; Specification/ Requirements and CoEvolution Architecture 15 STS: TID
| Work Package Title | Specification/ Requirements and CoEvolution Architecture 1 ICCS: AI model STR Αssessment., Εnhancement and Context Awareness technology enablers
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 18 | 14 | 33 | 16 | 10 | 0 | 33 | 28 | 24 | 0 | 6 | 24 | 4 | 0 | #ERROR! | #ERROR!
| Start month | AI model STR Αssessment., Εnhancement and Context Awareness technology enablers 1 ICCS: 8; AI model STR Αssessment., Εnhancement and Context Awareness technology enablers 8 UNIPI: End month; AI model STR Αssessment., Εnhancement and Context Awareness technology enablers 15 STS: 33
| Work Package Number | AI model STR Αssessment., Εnhancement and Context Awareness technology enablers 1 ICCS: WP5; AI model STR Αssessment., Εnhancement and Context Awareness technology enablers 9 SAP: Lead beneficiary; AI model STR Αssessment., Εnhancement and Context Awareness technology enablers 15 STS: DIE
| Work Package Title | AI model STR Αssessment., Εnhancement and Context Awareness technology enablers 1 ICCS: CoEvolution AI model lifecycle STR Security Assurance and Monitoring
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 16 | 21 | 8 | 0 | 0 | 12 | 20 | 18 | 0 | 16 | 0 | 6 | 20 | 14 | #ERROR! | #ERROR!
| Start month | CoEvolution AI model lifecycle STR Security Assurance and Monitoring 1 ICCS: 8; CoEvolution AI model lifecycle STR Security Assurance and Monitoring 8 UNIPI: End month; CoEvolution AI model lifecycle STR Security Assurance and Monitoring 15 STS: 33
| Work Package Number | CoEvolution AI model lifecycle STR Security Assurance and Monitoring 1 ICCS: WP6; CoEvolution AI model lifecycle STR Security Assurance and Monitoring 9 SAP: Lead beneficiary; CoEvolution AI model lifecycle STR Security Assurance and Monitoring 15 STS: AVI
| Work Package Title | CoEvolution AI model lifecycle STR Security Assurance and Monitoring 1 ICCS: Integration, evaluation and project outcomes
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 12 | 5 | 4 | 10 | 15 | 10 | 4 | 4 | 4 | 9 | 4 | 17 | 7 | 4 | #ERROR! | #ERROR!
| Start month | Integration, evaluation and project outcomes 1 ICCS: 6; Integration, evaluation and project outcomes 8 UNIPI: End month; Integration, evaluation and project outcomes 15 STS: 36
| Work Package Number | Integration, evaluation and project outcomes 1 ICCS: WP7; Integration, evaluation and project outcomes 9 SAP: Lead beneficiary; Integration, evaluation and project outcomes 15 STS: #N/A
| Work Package Title | Integration, evaluation and project outcomes 1 ICCS: #N/A
| Participant number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Participant Short Name | ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
| PMs per Participant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #ERROR! | #ERROR!
| Start month | #N/A 1 ICCS: #N/A; #N/A 8 UNIPI: End month; #N/A 15 STS: #N/A

## Table3.1c Deliverables
to sort by date | # | Name | Short description | WP# | Lead | Type | Diss. level | Del. date | For WP tables | MONTH | #DELIV
M03 | D1.1 | Project Manual | Project processes for day-to-day operations and quality management | 1 | ICCS | R | PU | M03 | D1.1:Project Manual (ICCS;R)
M06 | D1.2 | Data Management Plan | Data management plan (living document) | 1 | AEGIS | DMP | SEN | M06 | D1.2:Data Management Plan (AEGIS;DMP)
M06 | D2.1 | Plan for impact delivery | Communication, Dissemination and Exploitation Plan | 2 | AEGIS | R | SEN | M06 | D2.1:Plan for impact delivery (AEGIS;R)
M12 | D3.1 | Project scope definition | State of the art report, threat models, codified requirements and use cases | 3 | SAP | R | PU | M12 | D3.1:Project scope definition (SAP;R)
M12 | D3.2 | Technical specifications | Architecture and technical specification of the framework (live document) | 3 | ISI | OTHER | PU | M12 | D3.2:Technical specifications (ISI;OTHER)
M18 | D2.2 | First Impact Analysis | First report on the activities and indications on their impact | 2 | CBRL | R | SEN | M18 | D2.2:First Impact Analysis (CBRL;R)
M18 | D4.1 | Enablers development S&T report | Scientific and technical report of the developed tools and techniques | 4 | UNICA | R | PU | M18 | D4.1:Enablers development S&T report (UNICA;R)
M18 | D5.1 | Security assurance and monitoring S&T report | Scientific and technical report of the developed tools and techniques | 5 | ISI | R | PU | M18 | D5.1:Security assurance and monitoring S&T report (ISI;R)
M24 | D6.1 | Simulator & datasets | Simulator and datasets to support R&D | 6 | AVI | OTHER | PU | M24 | D6.1:Simulator & datasets (AVI;OTHER)
M24 | D6.2 | MVP | A minimum viable product of the integrated framework to be validated and demonstrated | 6 | AEGIS | OTHER | PU | M24 | D6.2:MVP (AEGIS;OTHER)
M33 | D4.2 | Enablers repository | SW repository with developed tools with proper documentation for prospective uptakers | 4 | TID | OTHER | PU | M33 | D4.2:Enablers repository (TID;OTHER)
M33 | D5.2 | Security assurance and monitoring repository | SW repository with developed tools with proper documentation for prospective uptakers | 5 | DIE | OTHER | PU | M33 | D5.2:Security assurance and monitoring repository (DIE;OTHER)
M36 | D1.3 | Innovation management report | Innovation management report | 1 | AEGIS | R | SEN | M36 | D1.3:Innovation management report (AEGIS;R)
M36 | D2.3 | Final Impact report | Second report on the activities and indications on their impact | 2 | CBRL | R | SEN | M36 | D2.3:Final Impact report (CBRL;R)
M36 | D6.3 | Integrated framework | Final integrated framework and prototypes | 6 | SIE | DEM | PU | M36 | D6.3:Integrated framework (SIE;DEM)
M36 | D6.4 | Evaluation report | Evalution process summary results for uptake and post-implementation support & development | 6 | SLC | R | PU | M36 | D6.4:Evaluation report (SLC;R)
|  | ICCS | 1
|  | UNICA | 1
0
|  | AEGIS | 4
|  | UNIPI | 0
|  | SLC | 1
|  | SAP | 1
|  | AVI | 1
0
|  | IMT | 0
|  | CBRL | 2
|  | #REF! | 0
SIE

## Table3.1d_Milestones
# | Name | Related WP | Due Date | Means of verification | Lead
MS1 | Project bootstrapping | WP1&2 | M06 | D1.1,D1.2&D2.1
MS2 | Project scope codification | WP3 | M12 | D3.1&D3.2
MS3 | R&D and impact maximization plans and first results | WP2,4&5 | M18 | D2.2,D4.1&D5.1
MS4 | MVP release | WP5 | Μ24 | D6.1&D6.2
MS5 | S&T outputs for uptake | WP4&5 | M33 | D4.2&D5.2
MS6 | Project outputs, evaluation and sustainability | WP1,2&6 | M36 | D1.3,D2.3,D6.3&D6.4
MS7
MS8
MS9
MS10

## Table3.1f
| WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | Total PMs | DO NOT DELETE
1-ICCS | 19 | 2 | 2 | 18 | 16 | 12 | 69 | 1 | ICCS | 6 | WPs!$F$1 | WPs!$F$200
2-ISI | 8 | 7 | 10 | 14 | 21 | 5 | 65 | 2 | ISI | 7 | WPs!$G$1 | WPs!$G$200
3-UNICA | 1 | 2 | 4 | 33 | 8 | 4 | 52 | 3 | UNICA | 8 | WPs!$H$1 | WPs!$H$200
4-IMT | 1 | 4 | 3 | 16 | 0 | 10 | 34 | 4 | IMT | 9 | WPs!$I$1 | WPs!$I$200
5-SIE | 1 | 9 | 3 | 10 | 0 | 15 | 38 | 5 | SIE | 10 | WPs!$J$1 | WPs!$J$200
6-AEGIS | 7 | 8 | 6 | 0 | 12 | 10 | 43 | 6 | AEGIS | 11 | WPs!$K$1 | WPs!$K$200
7-TID | 3 | 5 | 2 | 33 | 20 | 4 | 67 | 7 | TID | 12 | WPs!$L$1 | WPs!$L$200
8-UNIPI | 1 | 2 | 3 | 28 | 18 | 4 | 56 | 8 | UNIPI | 13 | WPs!$M$1 | WPs!$M$200
9-SAP | 1 | 7 | 7 | 24 | 0 | 4 | 43 | 9 | SAP | 14 | WPs!$N$1 | WPs!$N$200
10-SLC | 1 | 4 | 4 | 0 | 16 | 9 | 34 | 10 | SLC | 15 | WPs!$O$1 | WPs!$O$200
11-PAN | 1 | 10 | 4 | 6 | 0 | 4 | 25 | 11 | PAN | 16 | WPs!$P$1 | WPs!$P$200
12-AVI | 1 | 4 | 3 | 24 | 6 | 17 | 55 | 12 | AVI | 17 | WPs!$Q$1 | WPs!$Q$200
13-DIE | 1 | 6 | 6 | 4 | 20 | 7 | 44 | 13 | DIE | 18 | WPs!$R$1 | WPs!$R$200
14-CBRL | 1 | 12 | 4 | 0 | 14 | 4 | 35 | 14 | CBRL | 19 | WPs!$S$1 | WPs!$S$200
15-STS | 1 | 8 | 2 | 0 | 10 | 5 | 26 | 15 | STS | 20 | WPs!$T$1 | WPs!$T$200
Total PMs | 48 | 90 | 63 | 210 | 161 | 114 | 686

## Table 3.1g
Participant sort name | Cost (€) | Justification
Subcontracting
Participant sort name | Cost (€) | Justification
Subcontracting
Participant sort name | Cost (€) | Justification
Subcontracting

## Table 3.1h
Table requred for 0 Parnters: |  | #NAME?
| Cost (€) | Justification
Travel and subsistence |  | 20,000€ Travel costs for participation in all project’s meetings, 15,000€ Conferences & Open access papers
Equipment |  | 2 PCs for software development
Other goods, works and services |  | Licenses for SW frameworks and development environments
Remaining purchase costs (<15% of pers. Costs)
Total | 0
| Cost (€) | Justification
Travel and subsistence |  | 20,000€ Travel costs for participation in all project’s meetings, 15,000€ Conferences & Open access papers
Equipment |  | 2 PCs for software development
Other goods, works and services |  | Licenses for SW frameworks and development environments
Remaining purchase costs (<15% of pers. Costs)
Total | 0
| Cost (€) | Justification
Travel and subsistence |  | 20,000€ Travel costs for participation in all project’s meetings, 15,000€ Conferences & Open access papers
Equipment |  | 2 PCs for software development
Other goods, works and services |  | Licenses for SW frameworks and development environments
Remaining purchase costs (<15% of pers. Costs)
Total | 0

## Table3.1i
Participant Number/Short Name
| Cost (€) | Justification
Internally invoiced goods and services

## Table3.1j
Participant Number/Short Name
Third party name | Category | Cost (€) | Justification
Select between Seconded personnel Travel and subsistence Equipment Other goods, works and services Internally invoiced goods and services

## complimentarity
| ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
Obj#1 | bar: ICCS to ISI; IMT; AEGIS; UNIPI; SLC; DIE to STS
Obj#2 | bar: ISI to UNICA; SAP; AVI; CBRL
Obj#3 | bar: ISI to UNICA; SAP; AVI; CBRL
Obj#4 | bar: ICCS; UNICA to SIE; TID to UNIPI; AVI; STS
Obj#5 | bar: ISI; AEGIS; SLC; AVI to STS
Obj#6 | bar: SIE; PAN
Obj#7 | bar: SIE to TID; SAP; PAN to STS
| ICCS | ISI | UNICA | IMT | SIE | AEGIS | TID | UNIPI | SAP | SLC | PAN | AVI | DIE | CBRL | STS
AI systems | bar: ICCS; IMT to SIE; TID to UNIPI; AVI
ML robustness | bar: ISI to UNICA; SAP; AVI; CBRL
Cybersecurity systems | bar: ISI; AEGIS; SLC; DIE to STS
Privacy | bar: ICCS; UNIPI to SAP
Context-awareness | bar: UNICA to IMT; TID; STS
Application domain expertise | bar: SIE; PAN
Objective 1: Establish a comprehensive risk and security assessment engine for the complete lifecycle of an AI model in a supply chain and beyond.
Objective 2: Provide a Security, Trust and Robustness (STR) Defence Framework offering holistic AI model security-by-design approach throughout its overall lifecycle and under any AI realization paradigm (single, collaborative learning or interconnected AI agents supply chain).
Objective 3: Introduce and support a new paradigm on Security, Trust and Robustness for AI models compliant to the EU approach on AI and propose the AI Model Bills of Material as a universal AI Model description structure.
Objective 4: Infuse into the overall AI model design operation continuum (design, training, deployment) context awareness mechanism that allow a deployed AI model to be aware of its constantly evolving cybersecurity environment and adapt to adversaries based on such a context.
Objective 5: Provide the foundation and create the momentum for an STR AI supply chain ecosystem that offers to the AI community the CoEvolution hub of secure, trusted and robust AI models, trusted training datasets as well as the framework to utilize them in various AI paradigms (collaborative learning) and the AI supply chain.
Objective 6: Integrate, validate and assess the CoEvolution overall solution in 2 complex pilots that feature all AI model realization paradigms (i.e. single, collaborative learning and Interconnected AI agents) showcasing the security of the overall AI supply chain.
Objective 7: Provide a viable and well-structured business plan on the exploitation of the CoEvolution solution that will lead into a sustainable exploitable outcome after the duration of the project.

## Table3.4c (hidden)
Cost Chapter | Amount | %
Personnel | 4896901.2 | 74.35%
Travel and Subsistence | 301600 | 4.579%
Other Direct Costs | 67000 | 1.017%
Overhead | 1320625.3 | 20.05%
Total Project Costs | 6586126.5 | 100%
EC Requestred Contribution | 5989877 | 90.95%

## Table3.4d (hidden)
Nr | Partner | Total PMs | Personnel | Travel | Audit | Equipment | Overhead | Total
1 | ICCS | 69 | 345000 |  | 20000 | 5000 |  | 370000 | ICCS | 345000 | 25000 | 92500 | 462500
2 | ISI | 65 | 325000 |  | 20000 | 5000 |  | 350000 | ISI | 325000 | 25000 | 87500 | 437500
3 | UNICA | 52 | 260000 |  | 20000 | 0 |  | 280000 | UNICA | 260000 | 20000 | 70000 | 350000
4 | IMT | 34 | 221000 |  | 20000 | 0 |  | 241000 | IMT | 221000 | 20000 | 60250 | 301250
5 | SIE | 38 | 462840 |  | 20000 | 20000 |  | 502840 | SIE | 462840 | 40000 | 125710 | 628550
6 | AEGIS | 43 | 318200 |  | 20000 | 0 |  | 338200 | AEGIS | 318200 | 20000 | 84550 | 422750
7 | TID | 67 | 503411.2 |  | 20000 | 0 |  | 523411.2 | TID | 503411.2 | 20000 | 130852.8 | 654264
8 | UNIPI | 56 | 263200 |  | 20000 | 0 |  | 283200 | UNIPI | 263200 | 20000 | 70800 | 354000
9 | SAP | 43 | 344000 |  | 21600 | 0 |  | 365600 | SAP | 344000 | 21600 | 91400 | 457000
10 | SLC | 34 | 207400 |  | 20000 | 0 |  | 227400 | SLC | 207400 | 20000 | 56850 | 284250
11 | PAN | 25 | 303250 |  | 20000 | 0 |  | 323250 | PAN | 303250 | 20000 | 80812.5 | 404062.5
12 | AVI | 55 | 302500 |  | 20000 | 0 |  | 322500 | AVI | 302500 | 20000 | 80625 | 403125
13 | DIE | 44 | 286000 |  | 20000 | 0 |  | 306000 | DIE | 286000 | 20000 | 76500 | 382500
14 | CBRL | 35 | 297500 |  | 20000 | 0 |  | 317500 | CBRL | 297500 | 20000 | 79375 | 396875
15 | STS | 26 | 457600 |  | 20000 | 3000 |  | 480600 | STS | 457600 | 23000 | 120150 | 600750
Totals |  | 686 | 4896901.2 | 0 | 281600 | 30000 | 0 | 4750901.2

## PartA Data (hidden)
# | Participant Short name | (A) Direct personnel costs/€ | (B) Other direct costs/€ | (C) Direct costs of sub- contracting /€ | (D) Direct costs of providing financial support to third parties/€ | (E) Costs of inkind contributions not used on the beneficiary's premises/€ | (F) Indirect Costs/€ (=0.25(A+B-E)) | (G) Special unit costs covering direct & indirect costs | (H) Total estimated eligible costs/€ (=A+B+C+D+F +G) | (I) Reimburse- ment rate | (J) Max. grant / € (=H*I) | (K) Requested grant / €
1 | ICCS | 345000 | 29000 |  |  | 0 | 93500 | #ERROR! | 467500 | 100% | 467500 | 467500
3 | ISI | 325000 | 30000 |  |  | 0 | 88750 | #ERROR! | 443750 | 100% | 443750 | 443750
18 | UNICA | 260000 | 20000 |  |  | 0 | 70000 | #ERROR! | 350000 | 100% | 350000 | 350000
6 | IMT | 221000 | 20000 |  |  | 0 | 60250 | #ERROR! | 301250 | 100% | 301250 | 301250
8 | SIE | 462840 | 45000 |  |  | 0 | 126960 | #ERROR! | 634800 | 100% | 634800 | 634800
10 | AEGIS | 318200 | 25000 |  |  | 0 | 85800 | #ERROR! | 429000 | 100% | 429000 | 429000
9 | TID | 503411.2 | 25000 |  |  | 0 | 132102.8 | #ERROR! | 660514 | 100% | 660514 | 660514
12 | UNIPI | 263200 | 20000 |  |  | 0 | 70800 | #ERROR! | 354000 | 100% | 354000 | 354000
17 | SAP | 344000 | 38600 |  |  | 0 | 95650 | #ERROR! | 478250 | 100% | 478250 | 478250
4 | SLC | 207400 | 20000 |  |  | 0 | 56850 | #ERROR! | 284250 | 100% | 284250 | 284250
14 | PAN | 303250 | 20000 |  |  | 0 | 80812.5 | #ERROR! | 404062.5 | 100% | 404062.5 | 404062.5
#REF! | AVI | 302500 | 20000 |  |  | 0 | 80625 | #ERROR! | 403125 | 100% | 403125 | 403125
5 | DIE | 286000 | 20000 |  |  | 0 | 76500 | #ERROR! | 382500 | 100% | 382500 | 382500
#REF! | CBRL | 297500 | 20000 |  |  | 0 | 79375 | #ERROR! | 396875 | 100% | 396875 | 396875
|  | 4439301.2 | 352600 | 0 | 0 | 0 | 1197975.3 | #ERROR! | 5989876.5 |  | 5989876.5 | 5989876.5

## charts (hidden)
# | ShortNAme | Type | Country | totalBudget | Effort | Activity Type | Efforty | %
1 | ICCS | Research | EL | 4000 | 69 | Management | 90 | #ERROR!
2 | ISI | Research | EL | 5000 | 65 | Technical | #ERROR! | #ERROR!
3 | UNICA | Research | IT | 0 | 52 | Dissemination | #ERROR! | #ERROR!
4 | IMT | Research | FR | 0 | 34 |  | #ERROR!
5 | SIE | Industry | DE | 5000 | 38
6 | AEGIS | SME | DE | 5000 | 43
7 | TID | Industry | ES | 5000 | 67
8 | UNIPI | Research | IT | 0 | 56
9 | SAP | Industry | DE | 17000 | 43
10 | SLC | SME | IE | 0 | 34
11 | PAN | Industry | DE | 0 | 25
12 | AVI | SME | EL | 0 | 55
13 | DIE | SME | EL | 0 | 44
14 | CBRL | SME | CY | 0 | 35
660