## Sheet1
Possible start date
# | Name | Short description | Lead | Type | Del. date |  | 2024-07-01 | 2024-09-01 | 2024-10-01 | 2024-11-01
D1.1 | Project Manual | Project processes for day-to-day operations and quality management | ICCS | R | M03 | 3 | 2024-09-30 | 2024-11-30 | 2024-12-31 | 2025-01-31
D1.2 | Data Management Plan | Data management plan (living document) | AEGIS | DMP | M06 | 6 | 2024-12-31 | 2025-02-28 | 2025-03-31 | 2025-04-30
D2.1 | Plan for impact delivery | Communication, Dissemination and Exploitation Plan | AEGIS | R | M06 | 6 | 2024-12-31 | 2025-02-28 | 2025-03-31 | 2025-04-30
D3.1 | Project scope definition | State of the art report, threat models, codified requirements and use cases | SAP | R | M12 | 12 | 2025-06-30 | 2025-08-31 | 2025-09-30 | 2025-10-31
D3.2 | Technical specifications | Architecture and technical specification of the framework (live document) | ISI | OTHER | M12 | 12 | 2025-06-30 | 2025-08-31 | 2025-09-30 | 2025-10-31
D2.2 | First Impact Analysis | First report on the activities and indications on their impact | CBRL | R | M18 | 18 | 2025-12-31 | 2026-02-28 | 2026-03-31 | 2026-04-30
D4.1 | Enablers development S&T report | Scientific and technical report of the developed tools and techniques | UNICA | R | M18 | 18 | 2025-12-31 | 2026-02-28 | 2026-03-31 | 2026-04-30
D5.1 | Security assurance and monitoring S&T report | Scientific and technical report of the developed tools and techniques | ISI | R | M18 | 18 | 2025-12-31 | 2026-02-28 | 2026-03-31 | 2026-04-30
D6.1 | Simulator & datasets | Simulator and datasets to support R&D | AVI | OTHER | M24 | 24 | 2026-06-30 | 2026-08-31 | 2026-09-30 | 2026-10-31
D6.2 | MVP | A minimum viable product of the integrated framework to be validated and demonstrated | AEGIS | OTHER | M24 | 24 | 2026-06-30 | 2026-08-31 | 2026-09-30 | 2026-10-31
D4.2 | Enablers repository | SW repository with developed tools with proper documentation for prospective uptakers | TID | OTHER | M33 | 33 | 2027-03-31 | 2027-05-31 | 2027-06-30 | 2027-07-31
D5.2 | Security assurance and monitoring repository | SW repository with developed tools with proper documentation for prospective uptakers | DIE | OTHER | M33 | 33 | 2027-03-31 | 2027-05-31 | 2027-06-30 | 2027-07-31
D1.3 | Innovation management report | Innovation management report | AEGIS | R | M36 | 36 | 2027-06-30 | 2027-08-31 | 2027-09-30 | 2027-10-31
D2.3 | Final Impact report | Second report on the activities and indications on their impact | CBRL | R | M36 | 36 | 2027-06-30 | 2027-08-31 | 2027-09-30 | 2027-10-31
D6.3 | Integrated framework | Final integrated framework and prototypes | SIE | DEM | M36 | 36 | 2027-06-30 | 2027-08-31 | 2027-09-30 | 2027-10-31
D6.4 | Evaluation report | Evalution process summary results for uptake and post-implementation support & development | SLC | R | M36 | 36 | 2027-06-30 | 2027-08-31 | 2027-09-30 | 2027-10-31