## Slide 1: Partner AEGIS
Task 1.4 - Innovation tracking and data management
Identification of innovation generated by the project (innovation database)
Consolidation of background provided by Project Partners (mapping)
Update of data and assumptions presented in the proposal and the GA
IPR management of the project results
Identification of opportunities for realising innovations -> exploitation
Establishment of open science and data management planning activities
Identification of the relevant information that can be shared among the scientific communities for research purposes
Identification of the procedures for preserving and releasing project’s open assets even beyond the end of the project
Regular meetings
Identification of the Innovation Committee members
Decide how to handle Open Science commitments
Prepare IMP and DMP
Deliverables:
D1.2 Data Management Plan (M6)
D1.3 Innovation management and ethics oversight report (M36)

## Slide 2: Partner AEGIS
Task 1.5 - Ethical principles and European regulations, fundamental rights, and social sciences
Identify and analyse the applicable normative framework regarding ethics and privacy (Charter of Fundamental Rights of the EU, GDPR, Cyber resilience Act, AI Act, Protection of Privacy and Transborder Flows of Personal Data, Protection of personal data used for scientific research and statistics, Principle of equal treatment for men and women)
Ensure compliance with the relevant ethics and privacy requirements (especially regarding any personal data processing activities, compliance with the relevant GDPR principles)
Support the adoption of efficient procedures for evidence-based monitoring of compliance (e.g., GDPR audits, reporting and documentation, circulation of relevant questionnaires, scheduling of regular joint meetings, conduction of a DPIAs)
Establish an Ethical Board (constituted by internal and external experts) in order to quickly solve any issues without affecting the project outcomes
Deliverables:
D1.4 Analysis of the legal and ethical issues (M12)