## Slide 1: Partner AEGIS
Task 2.1 - Outreach planning, Communication and Dissemination
Leader: AEGIS
Participants: ALL
Duration: M1-M36
Objectives:
Plan and execute all the dissemination and communications activities
Monitor relevant KPIs and revise plans (if needed)
Raise awareness of CoEvolution objectives and vision
Organise webinars/workshops for knowledge-transfer, receive feedback and foster discussions

## Slide 2: Partner AEGIS
Task 2.1 - Outreach planning, Communication and Dissemination
Related Deliverable
Deliverable Number | D2.1 | Lead Beneficiary | AEGIS
Deliverable Name | Plan for impact delivery |  | 
Type | R — Document, report | Dissemination Level | SEN - Sensitive
Due Date (month) | 6 | Work Package No | WP2
Description |  |  | 
Communication, Dissemination and Exploitation Plan |  |  | 

## Slide 3: Partner AEGIS
Task 2.1 - Outreach planning, Communication and Dissemination
Dissemination & Communication activities
D&C
Website
A single-entry point to all the information about the project
Social media
Amplify CoEvolution web-based presence and communicate its message online. Twitter account, LinkedIn profile (more?)
Dissemination material
PowerPoint presentations, flyer, brochure.
Updated versions on regular basis
Publications
Papers and articles associated with the use-cases and key outcomes of the project
Events
Workshops, symposia, conferences etc.

## Slide 4: Partner AEGIS
Task 2.1 - Outreach planning, Communication and Dissemination
Dissemination KPIs
Scientific Publications | Papers in peer-reviewed Journals: ≥10
 | Presentations in Scientific Conference: ≥20
Technical Publications & White Papers | Technical articles: ≥10
 | White papers/factsheets: ≥10
Source Code Repository | Public Deliverables: 10
 | Open-source code: Publish to 2 repositories (e.g., GitHub, GitLab)
Workshops, webinars, and trainings | Use Case Workshops: 2; Technical Workshops: 2; Average number of attendees per workshop: >50
 | Online Training Tutorials: 3; Summer schools: 2; Webinars: 3; Industrial panels: 3; Enrolled users: >500
Push results to Communities, fora, alliances, and associations | High-impact communities/associations where to push CoEvolution results: >15
Industrial exhibitions, Trade Fairs | Industrial exhibitions targeted: ≥10
 | Roll-up banners: 2; Brochures to stakeholders: >1.000
Showcases | Showcasing events: ≥4; Different Countries Involved: ≥4; Participants: >400
Website | Online by: M01
 | Visitors at M36: >10.000
Social Media | Social media followers (by M36): >2.000
 | No. of impressions (monthly average): >500
e-Newsletters and Email Campaigns | e-Newsletters contributed/released: >6
 | Total Mailing List Contact Points: >1.000
Online Publishing | Press releases: ≥10
 | Events organised by local authorities: ≥3; People per event: >50
Promotional material | No. of hard copies (i.e., brochures, flyers, posters, etc.) distributed: >2.000
 | Roll-up Banners: >4
Multimedia | Number of promotional videos: >3; Number of interviews produced: >6; Views: >3.000
Public Talks | Public events at universities: ≥6; Students per event: >100; Open days: ≥6; Visitors/open day: >50
Communication KPIs

## Slide 5: Partner AEGIS
Task 2.1 - Outreach planning, Communication and Dissemination
Next Steps
Set up official project website (M1)
  coevolution-project.eu or coevolution-heu.eu or other…
Set up social media accounts & corresponding posts
Plan partners’ contributions
Create first version of dissemination material (updated regularly)