## Φύλλο1
[6 empty] | Due Date |  |  | Reviewers
No | Deliverable | Name | WP# | Lead Beneficiary | Type | Month | Date | Draft | Reviewer #1 partner name | Reviewer #1 person name | Reviewer #2 partner name | Reviewer #2 person name | Submitted Status
1 | D1.1 | Project Manual | WP1 | ICCS | R | M03 | 2025-01-31 | Completed | ISI | Apostolos Fournaris | AEGIS | Nikolaos Gkatzios | Submitted | ICCS | 3
2 | D1.2 | Data Management Plan | WP1 | AEGIS | DMP | M06 | 2025-04-30 |  | CBRL | Andreas Miaoudakis | BEVD | Omar Veledar |  | ISI | 3
3 | D1.3 | Innovation management and ethics oversight report | WP1 | AEGIS | R | M36 | 2027-10-31 |  | UNIPI | Antonio Carta | AVI | Aris Lalos |  | UNICA | 2
4 | D1.4 | Analysis of the legal and ethical issues | WP1 | AEGIS | R | M12 | 2025-10-31 |  | DIE | Entrit Metai | SLC | Christos Papadopoulos |  | UPatras | 2
5 | D2.1 | Plan for impact delivery | WP2 | AEGIS | R | M06 | 2025-04-30 |  | ICCS | Antonis Makris | TID | Carlos Segura |  | SIE | 2
6 | D2.2 | First Impact Analysis | WP2 | CBRL | R | M18 | 2026-04-30 |  | SLC | Christos Papadopoulos | AVI | Aris Lalos |  | AEGIS | 3
7 | D2.3 | Final Impact report | WP2 | CBRL | R | M36 | 2027-10-31 |  | ISI | Apostolos Fournaris | DIE | Entrit Metai |  | TID | 2
8 | D3.1 | Project scope definition | WP3 | ICCS | R | M12 | 2025-10-31 |  | AVL | David Lenk | STS | Ioannis Arakas |  | UNIPI | 2
9 | D3.2 | Technical specifications | WP3 | ISI | OTHER | M12 | 2025-10-31 |  | UNICA | Battista Biggio | UPatras | Georgios Bouloukakis |  | SLC | 2
10 | D4.1 | Enablers development S&T report | WP4 | UNICA | R | M18 | 2026-04-30 |  | AEGIS | Nikolaos Gkatzios | CBRL | Andreas Miaoudakis |  | AVL | 2
11 | D4.2 | Enablers repository | WP4 | TID | OTHER | M33 | 2027-07-31 |  | STS | Ioannis Arakas | BEVD | Omar Veledar |  | AVI | 2
12 | D5.1 | Security assurance and monitoring S&T report | WP5 | ISI | R | M18 | 2026-04-30 |  | UPatras | Georgios Bouloukakis | SIE | Arne Broering |  | DIE | 2
13 | D5.2 | Security assurance and monitoring repository | WP5 | DIE | OTHER | M33 | 2027-07-31 |  | AVL | David Lenk | BEVD | Omar Veledar |  | CBRL | 2
14 | D6.1 | Simulator & datasets | WP6 | AVI | OTHER | M24 | 2026-10-31 |  | ISI | Apostolos Fournaris | UNICA | Battista Biggio |  | STS | 2
15 | D6.2 | MVP | WP6 | UPatras | OTHER | M24 | 2026-10-31 |  | UNIPI | Antonio Carta | ICCS | Antonis Makris |  | BEVD | 3
16 | D6.3 | Integrated framework | WP6 | SIE | DEM | M34 | 2027-08-31 |  | ICCS | Antonis Makris | TID | Carlos Segura
17 | D6.4 | Evaluation report | WP6 | SLC | R | M36 | 2027-10-31 |  | SIE | Arne Broering | AEGIS | Nikolaos Gkatzios