## KPIs
KPI | Description | CURRENT | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
Scientific Publications KPIs
KPI 1 | Scientific papers in peer-reviewed Journals: ≥10 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 2 | Presentations in Scientific Conferences ≥20 | 1 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 1
Technical Publications & White Papers KPIs
KPI 3 | Published Technical articles: ≥10 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 4 | White papers/factsheets: ≥10 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Source Code Repository KPIs
KPI 5 | Public Deliverables: 10 | 1 | M6: 1; M7: 0; M8: 0
KPI 6 | Open-source code: Publish to 2 repositories (e.g., GitHub, GitLab) | 1 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 1; M6: 0; M7: 0; M8: 0
Push results to Communities, fora, alliances, and associations KPIs
KPI 7 | High-impact communities/associations where to push CoEvolution results: >15 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Showcases KPIs
KPI 8 | Showcasing events: ≥4 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 9 | Different Countries Involved: ≥4 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 10 | Participants: >400 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Workshops, webinars, and trainings KPIs (organised by the project)
KPI 11 | Use Case Workshops: 2 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 12 | Technical Workshops: 2 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 13 | Average number of attendees per workshop: >50 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 14 | Online Training Tutorials: 3 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 15 | Summer schools: 2 | 1 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 1; M8: 0
KPI 16 | Webinars: 3 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 17 | Industrial panels: 3 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 18 | Enrolled users: >500 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Industrial exhibitions, Trade Fairs KPIS
KPI 19 | Industrial exhibitions targeted: ≥10 | 1 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 1; M7: 0; M8: 0
KPI 20 | Roll-up banners: 2 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 21 | Brochures to stakeholders: >1.000 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Standardisation KPIs
KPI 22 | Number of standardization contributions to different SDOs with adoption status: ≥4 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Project Website KPIs
KPI 23 | Online by: M01 | YES | M1: yes
KPI 24 | Visitors at M36: >10.000 | 1093 | M1: 78; M2: 68; M3: 91; M4: 140; M5: 122; M6: 184; M7: 243; M8: 167
Social Media KPIs
KPI 25 | Social media followers (by M36): >2.000 | 299 | M6: 153; M7: 275; M8: 299
KPI 26 | No. of impressions (monthly average): >500 (we can only count LinkedIn) | 3414.8571 | M2: 5506; M3: 998; M4: 3962; M5: 1810; M6: 3052; M7: 4080; M8: 4496
e-Newsletters and Email Campaigns KPIs
KPI 27 | e-Newsletters contributed/released: >6 | 1 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 1
KPI 28 | Total Mailing List Contact Points: >1.000 | 26 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 15; M7: 24; M8: 26
Online Publishing KPIs
KPI 29 | Press releases: ≥10 | 1 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 1; M7: 0; M8: 0
KPI 30 | Events organised by local authorities: ≥3 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 31 | People per event: >50. | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Links and liaisons KPIs
KPI 32 | Number of DIH and clusters to contribute: 10 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 33 | Liaisons with other relevant projects: ≥5. | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Promotional material KPIs
KPI 34 | No. of hard copies (i.e., brochures, flyers, posters, etc.) distributed: >2.000 | 50 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 50; M8: 0
KPI 35 | Roll-up Banners: >4 | 1 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 1; M8: 0
Multimedia KPIs
KPI 36 | Number of promotional videos: >3 | 1 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 1; M7: 0; M8: 0
KPI 37 | Number of interviews produced: >6 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 38 | views: >3.000 | 28 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 28
Public Talks KPIs
KPI 39 | Public events at universities: ≥6 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 40 | Students per event: >100; | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 41 | Open days: ≥6 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
KPI 42 | Visitors/open day: >50 | 0 | M1: 0; M2: 0; M3: 0; M4: 0; M5: 0; M6: 0; M7: 0; M8: 0
Note on J22: Jihane Najar: CyberHot 2025
Note on I27: Jihane Najar: Future-Ready: On-Demand Solutions with AI, Data, and Robotics

## SM & Website
Project Month |  | X |  |  |  | LinkedIn | [5 empty] | Facebook |  |  |  | Bluesky |  |  | Website |  |  |  | Zenodo |  |  |  |  | YouTube
|  | Posts | likes & share & Comment | Followers (total) | Views | Posts | New Followers (monthly) | Page views | Unique visitors | Reactions | Impressions | Posts | Followers (Total) | Post reach | Views | Posts | Followers (Total) | likes & share & Comment | Visitors | Total visits | Downloads | Newsletter subscribers | Posts | Views (Total) | Views (Monthly) | Download (Total) | Downloads (Monthly) | Videos | Views | Subscribers (Total)
2024-11-01 | M1 | [17 empty] | 78 | 177
2024-12-01 | M2 | 3 | 23 | 15 | 275 | 3 |  |  |  |  | 5506 | [7 empty] | 68 | 74
2025-01-01 | M3 | 0 | 0 | 19 |  | 2 | 27 | 56 | 27 | 39 | 998 | [7 empty] | 91 | 276
2025-02-01 | M4 | 8 | 23 | 23 | 154 | 9 | 50 | 85 | 48 | 167 | 3962 | 12 | 6 | 107 | 173 |  |  |  | 140 | 295
2025-03-01 | M5 | 8 | 54 | 30 | 275 | 8 | 13 | 66 | 27 | 111 | 1810 | 8 | 14 | 68 | 116 | 2 | 4 |  | 122 | 136 |  | 15
2025-04-01 | M6 | 9 | 65 | 37 | 447 | 9 | 20 | 105 | 68 | 221 | 3052 | 9 | 22 | 112 | 170 | 9 | 7 | 5 | 184 | 213 | 3 | 15
2025-05-01 | M7 | 12 | 152 | 46 | 1072 | 14 | 9 | 62 | 38 | 282 | 4080 | 14 | 81 | 406 | 551 | 14 | 12 | 19 | 243 | 262 | 10 | 24 | 3 | 74 | 74 | 64 | 64 | 1 | 28 | 17
2025-06-01 | M8 | 10 | 109 | 50 | 844 | 10 | 9 | 96 | 48 | 249 | 4496 | 10 | 91 | 202 | 281 | 10 | 13 | 22 | 167 | 191 | 20 | 26 | 2 | 134 | 60 | 111 | 47 | 0 | 31 | 17
2025-07-01 | M9
2025-08-01 | M10
2025-09-01 | M11
2025-10-01 | M12
2025-11-01 | M13
2025-12-01 | M14
2026-01-01 | M15
2026-02-01 | M16
2026-03-01 | M17
2026-04-01 | M18
2026-05-01 | M19
2026-06-01 | M20
2026-07-01 | M21
2026-08-01 | M22
2026-09-01 | M23
2026-10-01 | M24
2026-11-01 | M25
2026-12-01 | M26
2027-01-01 | M27
2027-02-01 | M28
2027-03-01 | M29
2027-04-01 | M30
2027-05-01 | M31
2027-06-01 | M32
2027-07-01 | M33
2027-08-01 | M34
2027-09-01 | M35
2027-10-01 | M36
|  | 50 |  | 50 |  | 55 | 128 |  |  |  | 3414.8571 | 53 | 91 |  |  | 35 | 13 |  | 1093 |  |  |  | 5 |  |  |  |  | 1 |  | 17
23904
Total Followers | 299
Total Posts | 199

## Materials Plan
Newsletter | Deadline | Status | Date of Submission
1 | 2025-06-30 | Released | 2025-06-17 |  | White papers/factsheets | Topic | Deadline | Status | Date of Submission
2 | 2025-10-31 | Not Started |  |  | 1
3 | 2025-04-30 | Not Started |  |  | 2
4 | 2026-10-31 | Not Started |  |  | 3 |  | 2025-12-31
5 | 2027-04-30 | Not Started |  |  | 4
6 | 2027-10-31 | Not Started |  |  | 5
6
7
8
Press Release | Deadline | Status | Date of Submission | Topic | 9
1 | 2025-04-30 | Released | 2025-04-30 | Launch of the Project | 10
2 |  | Not Started
3 | TBD (October 2025) | Not Started |  | Invitation to the 1st Info Day
4 | 2025-10-31 | Not Started |  | One Year of the Project (e.g., CoEvolution Project Celebrates a Successful First Year of …)
5 | TBD (May-August 2026)) | Not Started |  | Invitation to the 2nd Info Day
6 |  | Not Started
7 | 2026-10-31 | Not Started |  | Two Years of the Project (e.g., CoEvolution Project Celebrates a Two Years of …)
8 |  | Not Started
9 |  | Not Started
10 | 2027-10-31 | Not Started |  | End of the Project
Roll-up Banner | Deadline | Status | Date of Submission
1 | 2025-06-30 | Ready | 2025-05-15
2 | 2025-10-31 | Not Started
3 | 2025-04-30 | Not Started
4 | 2026-10-31 | Not Started

## Sheet1 (hidden)
|  |  |  | Goal | M7 Status
|  |  |  | 2000 | 275
|  | Month | Website Visitors
|  | 2024-11-01 | 78
|  | 2024-12-01 | 68
|  | 2025-01-01 | 91
|  | 2025-02-01 | 140
|  | 2025-03-01 | 122
|  | 2025-04-01 | 184
|  | 2025-05-01 | 243
Month | Impressions
2024-12-01 | 5506
2025-01-01 | 998
2025-02-01 | 3962
2025-03-01 | 1810
2025-04-01 | 3052
2025-05-01 | 4080